## Dev Tasks
[5 empty] | Overall Status: | 100%
Demand | Phase | Task | SubTask | Completed | Date | Notes
DMNN12345 | Design | Process Design | Understand the overall process, idicate the challenges and re-engneering opportunity. | TRUE
|  |  | Determine the framework type and transaction item type. | TRUE
|  |  | Break down the process into modules, every workflow could run independently. | TRUE
|  |  | Look for reusable components and/or libraries. | TRUE
|  |  | Request sample data from the business and explore the data. | TRUE
|  |  | Identify test cases, including business requirements stated in the PDD and unit testing defined by the developer. | TRUE
|  | Design Review | Present the design to the team, address the items above. | TRUE
|  |  | Complete the Solution Design Document (SDD). | TRUE
|  |  | Create design review form in SharePoint. | TRUE
|  |  | Get sign-off and/or feedback from the reviewers. | TRUE
|  | Follow-up | Follow up on the action items from the initial design review. | TRUE
|  | Environment Setup | Create Github repository. | TRUE
|  |  | Create and protect develop branch. | TRUE
|  |  | Create project from framework template. | TRUE
|  |  | Create folder structure on local/shared drive for development and testing. | TRUE
| Build | Development Unit Testing | Test the framework end-to-end without any issue. | TRUE
|  |  | Build modules defined in the process design. | TRUE
|  |  | Unit testing, all pieces can be tested independently. | TRUE
|  |  | End-to-end functionality test. | TRUE
|  |  | Fit modules into the framework. | TRUE
|  |  | Check and fix the hard coded values, create assets as needed. | TRUE
|  |  | Move workflows into subfolders under process folder, avoid special characters in the file/folder name. | TRUE
|  |  | Remove unused variables/arguments/dependencies/workflows. | TRUE
|  |  | Perform end-to-end attended run, record the process for UAT. | TRUE
|  |  | Perform end-to-end unattended, export the logs for code review. | TRUE
|  | Code Review | Walk through the SDD and the code with the team. | TRUE
|  |  | Publish the code to DEV orchestrator. | TRUE
|  |  | Commit the code to Github, create pull request from develop to master. | TRUE
|  |  | Create code review form in SharePoint. | TRUE
|  |  | Create Change Request in ServiceNow. | TRUE
|  |  | Get feedback if any, get sign-off from the main reviewer on Github pull request, SharePoint code review form and Test task in change request. | TRUE
|  | Follow-up | Follow up on the action items from the initial code review. | TRUE
| Deploy | Deploy | Get approval for the change request. | TRUE
|  |  | Prepare asset/queue list, deploy to-to list and schedule implementation meeting with server admin. | TRUE
|  |  | Conduct production validation run if necessary. | TRUE

## Code Review
1. General Coding Standards
A. Naming Conventions
Variables follow camelCase or PascalCase.
Workflow names are descriptive and use PascalCase.
Arguments are prefixed with their direction (in_, out_).
Constants use all caps with underscores (e.g., MAX_RETRIES).
Selector variables are named clearly (e.g., btnSubmitSelector).
B. Commenting
Key logic is explained with inline comments.
Unused or deprecated code is commented out with an explanation.
Complex decision points are documented with comments.
Public workflows have XML comments for input/output.
Comments are concise and meaningful.
C. Organized Structure
Workflows are organized in folders by functionality (e.g., Data, Processes).
Reusable components are in a Libraries folder.
Temporary or test files are stored in a separate folder.
Project files are named consistently.
Documentation is stored in a dedicated Docs folder.
D. Readability
Code is properly indented (2 or 4 spaces).
Long expressions are broken into multiple lines.
Activities are arranged logically within workflows.
White space is used effectively for clarity.
Consistent font styles are applied throughout the project.
E. Version Control
Code is stored in a version control system (e.g., Git).
Commit messages are descriptive and follow a format.
Branching strategies are documented and followed.
Pull requests are used for code reviews.
Version history is regularly reviewed and cleaned up.
2. Workflow Design
A. Modular Design
Workflows are broken into reusable components.
Common tasks are encapsulated in library workflows.
Inputs/outputs for components are clearly defined.
Dependencies are managed appropriately.
Workflows have clear entry and exit points.
B. Error Handling
Try-Catch activities are used for exception management.
Specific exceptions are caught instead of general exceptions.
Custom error messages provide context for failures.
Critical paths have fallback mechanisms.
Error handling workflows are documented.
C. Input Validation
User inputs are validated for format and type.
Empty or null checks are implemented.
Default values are provided for optional inputs.
Validation feedback is user-friendly.
Data is sanitized before processing.
D. Flow Control
Decision structures (If, Switch) are used appropriately.
Flowcharts are used for complex logic.
Loops are optimized and not excessively nested.
Breakpoints are used for debugging and clarity.
State management is documented in workflows.
E. User Interaction
UI elements are interacted with reliably (e.g., clicks, types).
User prompts are clear and informative.
Wait times are minimized and based on UI responsiveness.
Keyboard shortcuts are used where possible.
User actions are logged for transparency.
3. Variables and Arguments
A. Scope Management
Variables are scoped appropriately (local vs. global).
Unused variables are removed or commented out.
Temporary variables have clear lifetimes.
Global variables are documented to avoid confusion.
Argument types are specified clearly.
B. Data Types
Correct data types are used for all variables (e.g., String, Int32).
Collections are initialized properly.
Type conversions are handled explicitly.
Data structures are used consistently (e.g., lists vs. arrays).
Type safety is enforced throughout the workflows.
C. Naming Consistency
Variable names are consistently styled (e.g., all camelCase).
Temporary variables are named clearly to reflect their use.
Constants are identified with a specific prefix (e.g., const_).
Argument names match their purpose throughout workflows.
Naming conventions are documented and adhered to.
D. Documentation
All variables and arguments are documented in the workflow.
Descriptions explain the purpose of key variables.
Changes to variables are logged and noted.
Variable lifetimes are documented in complex workflows.
Data flow diagrams are included in project documentation.
E. Initialization
Variables are initialized before use.
Collections have default values upon declaration.
Input parameters have default values defined where applicable.
No variable is used before assignment.
Temporary values are cleared after use.
4. Best Practices
A. Configuration Management
Configuration settings are stored in an external file (e.g., JSON, XML).
Paths and URLs are parameterized.
Default configurations are provided for different environments.
Environment variables are used for sensitive data.
Configuration files are documented.
B. Logging
Log levels are appropriately set (Info, Warn, Error).
All key actions and decisions are logged.
Logs are structured for easy searching and filtering.
Sensitive data is masked in logs.
Log retention policies are established.
C. Code Reusability
Common functionalities are abstracted into libraries.
Workflows are designed to be reusable with different inputs.
Repeated code segments are refactored into separate activities.
Shared components are versioned for compatibility.
Documentation highlights reusable components.
D. Testing and Quality Assurance
Unit tests cover critical functions and edge cases.
Integration tests are created for interconnected workflows.
Testing scenarios are documented and reviewed.
Continuous integration practices are in place.
Test results are logged and actionable.
E. Security Practices
Sensitive data is encrypted at rest and in transit.
Access controls are implemented for workflows.
Code reviews include security assessments.
Third-party libraries are vetted for vulnerabilities.
Security patches are applied promptly.
5. Performance Considerations
A. Activity Optimization
Redundant activities are removed or combined.
Minimize use of UI automation where possible.
Use of caching for data that doesn’t change frequently.
Appropriate use of parallel processing is implemented.
Avoid excessive logging in performance-critical areas.
B. Resource Management
Memory usage is monitored and optimized.
Unused resources are disposed of properly.
Long-running transactions are tracked and optimized.
Data retrieval processes are efficient (e.g., batching).
CPU-intensive tasks are offloaded or scheduled during off-peak hours.
C. Transaction Management
Transactions are handled atomically.
Rollback mechanisms are in place for failures.
Transaction logs are maintained for auditing.
Batch sizes are optimized for performance.
Deadlock scenarios are handled appropriately.
D. External Service Calls
Calls to external services are minimized.
Retry mechanisms are implemented for transient failures.
Service timeouts are configured appropriately.
Asynchronous calls are used when beneficial.
Monitoring of service call performance is in place.
E. Testing for Performance
Performance benchmarks are established for workflows.
Load testing is conducted for high-traffic processes.
Performance metrics are collected and analyzed.
Bottlenecks are identified and addressed.
Documentation of performance testing results is maintained.
6. Security Practices
A. Data Protection
Sensitive information is encrypted in storage and during transmission.
Access to sensitive data is restricted based on user roles.
Personal identifiable information (PII) is handled according to regulations.
Security policies are documented and enforced.
Data retention policies are implemented.
B. Credential Management
Credentials are stored securely using Orchestrator assets.
Multi-factor authentication (MFA) is implemented where feasible.
Access to credential storage is logged and monitored.
Regular audits of credential usage and access are conducted.
A process for credential rotation is established.
C. Access Control
Role-based access control (RBAC) is implemented for workflows.
User access is reviewed periodically and adjusted as needed.
Least privilege principle is applied for all users.
Access to sensitive workflows is restricted.
User activity is logged for accountability.
D. Code Security
Security reviews are part of the code review process.
Third-party libraries are checked for vulnerabilities.
Dependency management is regularly reviewed.
Security patches are applied promptly.
Secure coding practices are documented and followed.
E. Audit and Compliance
Regular audits of automation processes are conducted.
Compliance with industry regulations is ensured (e.g., GDPR, HIPAA).
Security incidents are logged and reported.
Compliance documentation is maintained and updated.
User training on security policies is provided regularly.
7. Testing and Validation
A. Unit Testing
Unit tests cover at least 80% of critical code paths.
Tests include both positive and negative scenarios.
Test cases are clearly documented.
Automated testing frameworks are used where possible.
Test data is isolated from production data.
B. Integration Testing
Integration tests cover workflows that interact with other systems.
Dependencies between workflows are clearly documented.
Test cases validate end-to-end scenarios.
Automated integration tests are in place for CI/CD pipelines.
Results of integration tests are logged and actionable.
C. User Acceptance Testing (UAT)
UAT scenarios are defined and documented.
Feedback from users is collected and addressed.
UAT sign-off is obtained before production deployment.
Users are trained on new features prior to UAT.
UAT results are reviewed and logged for future reference.
D. Performance Testing
Performance benchmarks are established for critical workflows.
Load testing is conducted under expected peak conditions.
Performance testing results are analyzed for bottlenecks.
Scalability tests are performed to ensure future growth.
Performance testing documentation is maintained.
E. Regression Testing
Regression tests are run before each major release.
Test suites are updated to reflect new functionality.
Automated regression tests are in place for stability.
Critical paths are included in regression tests.
Regression testing results are reviewed and documented.
8. Documentation
A. Project Overview
An executive summary of the project is provided.
Architectural diagrams are included to illustrate workflow interactions.
Dependencies on external systems are documented.
Team roles and responsibilities are outlined.
Key project milestones are tracked and reported.
B. Workflow Documentation
Each workflow has a description of its purpose and functionality.
Input and output parameters are documented.
Business rules implemented in workflows are clearly stated.
Change history is maintained for each workflow.
Visual aids (e.g., flowcharts) are included where necessary.
C. Configuration Documentation
Configuration settings are documented in detail.
Default values and their purposes are explained.
Changes to configurations are logged.
Instructions for updating configurations are clear.
Environment-specific configurations are highlighted.
D. User Documentation
User manuals are provided for end-users of the automation.
Troubleshooting guides are included.
Frequently asked questions (FAQs) are documented.
Training materials are created and distributed.
User feedback mechanisms are established.
E. Maintenance Documentation
Maintenance schedules are documented and communicated.
Known issues and resolutions are recorded.
Procedures for handling updates and upgrades are clear.
Backup and recovery procedures are documented.
Roles and responsibilities for maintenance tasks are defined.
9. Code Consistency
A. Coding Patterns
Common design patterns are identified and documented.
Patterns are applied consistently across the project.
Code examples for patterns are provided in documentation.
Review process includes checks for pattern consistency.
Refactoring efforts ensure adherence to patterns.
B. Style Guide
A style guide for coding practices is documented.
Code reviews assess adherence to the style guide.
New team members are trained on the style guide.
Updates to the style guide are communicated to the team.
The style guide is reviewed periodically for relevance.
C. Tooling
Development tools are standardized across the team.
Version control practices are uniformly applied.
Code quality tools (e.g., linters) are used consistently.
Automated code formatting tools are integrated.
Team feedback on tooling is solicited regularly.
D. Peer Reviews
All code changes undergo peer review before merging.
Reviewers provide constructive feedback.
Review process includes checks for adherence to standards.
Review metrics (e.g., time to review) are tracked.
Review outcomes are documented for future reference.
E. Continuous Improvement
Retrospectives are held to discuss coding practices.
Team members are encouraged to propose improvements.
Best practices are updated based on team feedback.
Lessons learned from projects are documented.
Continuous learning opportunities (e.g., workshops) are provided.
10. Change Management
A. Change Control Process
A formal process for requesting changes is in place.
All changes are logged and tracked.
Impact assessments are conducted for proposed changes.
Stakeholder approval is obtained for significant changes.
Change implementation is documented and communicated.
B. Versioning
Versioning is applied to all workflows and libraries.
Semantic versioning practices are followed (major.minor.patch).
Release notes are created for each version.
Backward compatibility is maintained where possible.
Deprecated features are clearly communicated.
C. Rollback Procedures
Rollback procedures are documented for critical changes.
Backup workflows are available for quick recovery.
Rollback tests are conducted periodically.
Stakeholders are informed about rollback capabilities.
Documentation includes steps for rollback execution.
D. Monitoring Changes
Changes are monitored post-implementation for issues.
Metrics are collected to assess the impact of changes.
Feedback from users is solicited after changes are made.
Documentation is updated to reflect any changes made.
Lessons learned from changes are recorded for future reference.
E. Training and Support
Training is provided for users impacted by changes.
Support channels are established for post-change queries.
FAQs are updated to include information on recent changes.
Feedback mechanisms for training effectiveness are in place.
Ongoing support resources are available for users.